## INTRO
The purpose of the PK12 Reopening Workbook, is to assist states and districts develop comprehensive plans for the reopening and operation of PK-12 schools for the 2020-21 school year, while our communities are at risk from the COVID 19 pandemic.
This workbook was developed through 8 live webinars facilitated and supported by the National Council on School Facilities, a non-profit organization dedicated to supporting states in their varied roles and responsibilities for safe, healthy, and educationally appropriate public school facilities that are equitable, sustainable and fiscally sound; and with Cooperative Strategies, a national educational facilities planning firm, and one of the industry partners of the National Council on School Facilities.
Over 100 Webinar participants, which included state and school districts officials, leaders from civic and labor organizations, private sector design, planning, and building professionals, as well as researchers participated in this process. The webinars were open to all and recorded. They can be found at www.facilitiescouncil.org.
This workbook will be updated and improved, we thank the participants whose comments and input have helped create this. This is Version 1.0 dated May 28, 2020.
This workbook is designed so that districts, states, and other planners can add or delete tasks; modify descriptions and other details and make the planning work for your community. There is an accompanying Reopening and Operating Workbook Version 1.0, May 28, 2020, also available at www.facilitiescouncil.org.

## Reopening Workbook
Strategies | What? needs to be done | who? needs to do it | where? does the task need to be done | when? does the task need to be done | how often? does the task need to be done | Task detailed descriprtion | Link to resource materials
Plan for social distancing of staff in schools and buses. | Plan for social distancing of staff in schools.
Plan for social distancing of staff in schools and buses. | Develop a protocols for social contact of adult staff within school before children return. E.g. less than ten persons in a room, 6 feet apart, with or without masks? | administrators |  | for reopening
Plan for social distancing of staff in schools and buses. | Develop protocols for social contact of adult staff with parents within school before children return. | administrators |  | for reopening
Plan for social distancing of staff in schools and buses. | Install protective clear plastic between adults so parents can interact with front office staff to register students ahead of school reopening. | outside contractor |  | for reopening
Plan for social distancing of staff in schools and buses. | Develop and post guidelines for visitors and parents who enter the school. | administrators |  | for reopening
Plan for social distancing of students in schools and buses. | Plan for social distancing of students in schools and buses.
Plan for social distancing of students in schools and buses. | Develop a useable instructional space plan for the recommended social distance of 6 feet of personal space. To consider: room characteristics for effective instruction--acoustics, daylight, access to materials and equipment | space planner
Plan for social distancing of students in schools and buses. | Determine the "Corona capacity" of each school building | space planner |  | for reopening
Plan for social distancing of students in schools and buses. | Collect data useful for capacity analysis. | facilities managers |  | for reopening
Plan for social distancing of students in schools and buses. | Current school capacities | facilities managers |  | for reopening
Plan for social distancing of students in schools and buses. | Class size multipliers by grade or subject | space planner |  | for reopening
Plan for social distancing of students in schools and buses. | Square footage of the school | facilities managers |  | for reopening
Plan for social distancing of students in schools and buses. | Square footage of classrooms and other instructional and common spaces. | facilities managers |  | for reopening
Plan for social distancing of students in schools and buses. | Identify potential areas to use to expand current capacities--for examples: art rooms, music rooms, cafeteria, gym, and school grounds. | space planner |  | for reopening
Plan for social distancing of students in schools and buses. | Propose an "on-site" corona capacity, which includes social distancing in traditional capacity spaces and use of instructional areas, not traditionally used for capacity calculations, such as cafeterias for instruction AND with capacities that would accommodate in seat instruction, but would not general have capacity, such as a gym or outdoor covered classroom. | space planner |  | for reopening
Plan for social distancing of students in schools and buses. | Calculate a corona utilization of each school using the 2019-20 enrollment and the corona capacity, to identify whether and which schools may need to reduce school schedule to achieve social distancing. | space planner |  | for reopening
Plan for social distancing of students in schools and buses. | Account for delivering special education classes, or social distancing of aids who accompany students in regular classes, where appropriate. | space planner |  | for reopening
Plan for social distancing of students in schools and buses. | Determine if it is physically possible to serve the fall 2020-21 enrollment of students projected to attend each school. | space planner |  | for reopening
Plan for social distancing of students in schools and buses. | Prepare a brief DRAFT report to local school communities--administration, teachers, and parents on whether and which school BUILDINGS can support corona capacities and seek input on the preliminary findings. | space planner |  | for reopening
Plan for social distancing of students in schools and buses. | Ask school administration to determine the feasibility of staffing the school at its corona capacity and report back to the central administration. | administrators |  | for reopening
Plan for social distancing of students in schools and buses. | Develop a school day class schedule to minimize room changes. | administrators |  | for reopening
Plan for social distancing of students in schools and buses. | Develop a lunch time plan to ensure lunch time maintains social distancing. | administrators |  | for reopening
Plan for social distancing of students in schools and buses. | Develop a staffing plan to support a social distancing schedule and social distancing space plan. | administrators |  | for reopening
Plan for social distancing of students in schools and buses. | Develop the special education plan to ensure appropriate service and educational delivery within the social distance environment. | teachers |  | for reopening
Plan for social distancing of students in schools and buses. | Ask student council to draft compliance guidelines to social distancing, and enhanced hygiene and cleaning protocols | students |  | for reopening
Plan for social distancing of students in schools and buses. | Evaluate the local school operational challenges to education delivery in a corona capacity school. | administrators |  | for reopening
Plan for social distancing of students in schools and buses. | IF reorganization of existing spaces using existing staff, cannot support corona capacity, then explore other mitigation options that support social distancing. | administrators |  | for reopening
Plan for social distancing of students in schools and buses. | Identify capital projects that can expand and support onsite corona capacity. | facilities managers |  | for reopening
Plan for social distancing of students in schools and buses. | Explore whether portable classrooms, roofed or tented outdoor classrooms, room conversions, or other projects enable school enrollment to be supported on site. | facilities managers |  | for reopening
Plan for social distancing of students in schools and buses. | Identify small cap projects, like expanding hand washing stations, bathroom renovations, nurses suite modifications to separate students, and front office changes to enable contact with parents. | facilities managers |  | for reopening
Plan for social distancing of students in schools and buses. | Make site improvements, like landscaping and outdoor structures to support outdoor classrooms and areas for social distancing. | facilities managers |  | for reopening
Plan for social distancing of students in schools and buses. | Prepare site markings outside with 6 foot markings on sidewalks, and play areas, mark with cones, ropes, to control large numbers of students. | facilities managers |  | for reopening
| Identify schedule and educational delivery scenarios to support onsite corona capacity. | community process |  | for reopening
Plan for social distancing of students in schools and buses. | Explore pros and cons of half day schedules hybrid of in school and on-line learning, reassignment to low utilized schools. | community process |  | for reopening
Plan for social distancing of students in schools and buses. | Explore pros and cons of split enrollment days some students at school MWF and other students in school Tu/Thr; and alternate 3 and 2 day weeks. | community process |  | for reopening
Plan for social distancing of students in schools and buses. | Explore pros and cons of 4 day school week with one day online learning--increasing school capacity by 20% | community process |  | for reopening
Plan for social distancing of students in schools and buses. | Estimate the staffing required to operate at recommended levels of social distancing for each scenario at HS, MS, and ES levels. | community process |  | for reopening
Plan for social distancing of students in schools and buses. | Identify student assignment changes that support onsite corona capacity. |  |  | for reopening
Plan for social distancing of students in schools and buses. | Determine whether the district has capacity in some schools, but not in others, which would enable students to attend re-opened schools without a schedule change--for example, crowded ES, but excess capacity in MS, so moving a grade into the next level school; | administrators |  | for reopening
Plan for social distancing of students in schools and buses. | Estimate the number of students who would need to be reassigned at recommended levels of social distancing. | administrators |  | for reopening
Plan for social distancing of students in schools and buses. | Evaluate transportation impact including capacity, schedule, and costs associated with social distancing schedule and student assignment proposals. | bus operators |  | for reopening
Plan for social distancing of students in schools and buses. | Establish school-level COVID committees of staff, parents, and students to help determine the feasibility of proposed reopening and operations, and to give ongoing input into the implementation and communication of the health, cleaning, and social distancing protocols, practices, and compliance with COVID related issues. | community process |  | for reopening
Plan for social distancing of students in schools and buses. | Prepare a feasibility study on corona building capacities, cap projects, schedule changes, and student assignment changes with schedule and budget assumptions, as well as input from school staff and community. | community process |  | for reopening
Plan for continued support and delivery of online instruction and home schooling related to other closures and social distancing constraints | Plan for continued support and delivery of online instruction and home schooling related to other closures and social distancing constraints | educators |  | for reopening
Plan for continued support and delivery of online instruction and home schooling related to other closures and social distancing constraints | Provide students with technology for online learning at home. | administrators
Plan for continued support and delivery of online instruction and home schooling related to other closures and social distancing constraints | Provide students with chrome books | administrators
Plan for continued support and delivery of online instruction and home schooling related to other closures and social distancing constraints | Provide students with hot spots | administrators
Plan for continued support and delivery of online instruction and home schooling related to other closures and social distancing constraints | Mail students curriculum packets to their homes | administrators
Plan for continued support and delivery of online instruction and home schooling related to other closures and social distancing constraints | Provide students and their families with food service delivered to pick up sites | administrators
Plan for continued support and delivery of online instruction and home schooling related to other closures and social distancing constraints | Provide students and families with food service for pick up at schools | administrators
Plan for continued support and delivery of online instruction and home schooling related to other closures and social distancing constraints | Establish and communicate school use guidelines to non-school users of public school facilities for 2020-21 school year. | administrators
Plan for continued support and delivery of online instruction and home schooling related to other closures and social distancing constraints | Increase security on vacant schools. | facilities managers
Plan for continued support and delivery of online instruction and home schooling related to other closures and social distancing constraints | Provide nurses to feeding sites | administrators
Plan for continued support and delivery of online instruction and home schooling related to other closures and social distancing constraints | Replace the technology that was issued and not returned from last school year. | administrators
Plan for continued support and delivery of online instruction and home schooling related to other closures and social distancing constraints | Increased level of food service when feeding families without income. | administrators
Plan for continued support and delivery of online instruction and home schooling related to other closures and social distancing constraints | Plan for community supports delivered through and at public schools. | administrators
Plan for continued support and delivery of online instruction and home schooling related to other closures and social distancing constraints | Provide space and support for community feeding programs | administrators
Plan for continued support and delivery of online instruction and home schooling related to other closures and social distancing constraints | Provide space and support for childcare for first responders, health care and other essential workers. | administrators
| Develop election day plans for ensuring healthy voting | administrators
Plan for increased levels of cleaning & disinfecting surfaces in schools and buses. | Plan for increased levels of cleaning & disinfecting surfaces in schools and buses. | facilities managers
Plan for increased levels of cleaning & disinfecting surfaces in schools and buses. | Determine custodial staff capacity to prepare and maintain schools to higher cleanliness and hygiene standards. | facilities managers
| Compare current levels of staffing per GSF to 10,000 SF per custodian for level 1 cleaning. | facilities managers
Plan for increased levels of cleaning & disinfecting surfaces in schools and buses. | Hire and train added custodians where needed. | facilities managers
Plan for increased levels of cleaning & disinfecting surfaces in schools and buses. | Prepare a training regime for current and new employees and contractors. | facilities managers
Plan for increased levels of cleaning & disinfecting surfaces in schools and buses. | Identify protections for custodial workers and contractors responsible for custodial protocols. | administrators
Plan for increased levels of cleaning & disinfecting surfaces in schools and buses. | Develop CHECK LIST for cleaning vacant schools before teachers and adult staff return. | facilities managers
Plan for increased levels of cleaning & disinfecting surfaces in schools and buses. | Clean and disinfect classrooms so teachers can declutter their rooms at the end of school year in preparation for setting up social distancing in classrooms and more intensive cleaning and disinfecting during the school year. | janitorial staff
Plan for increased levels of cleaning & disinfecting surfaces in schools and buses. | Teachers prepare their 2019-20 classrooms for higher levels of cleaning and social distancing environment--understanding that this room may not be assigned to them in the2020-21 school year. | teachers
Plan for increased levels of cleaning & disinfecting surfaces in schools and buses. | Declutter storage areas to prepare for the need for added storage to support corona capacities in schools. | janitorial staff
Plan for increased levels of cleaning & disinfecting surfaces in schools and buses. | Develop daily CHECK LIST for cleaning that includes regular cleaning and that addresses high, moderate and low risk levels for virus threats. (protocols) | facilities managers
Plan for increased levels of cleaning & disinfecting surfaces in schools and buses. | Teachers wipe down surfaces they have touched with disenfectant wipes before they leave each day. | teachers
Plan for increased levels of cleaning & disinfecting surfaces in schools and buses. | Custodians clean each room after staff leaves. | janitorial staff
Plan for increased levels of cleaning & disinfecting surfaces in schools and buses. | If a feeding site has staff with COVID, deep clean the site. | outside contractor
Plan for increased levels of cleaning & disinfecting surfaces in schools and buses. | Develop CHECK LIST for cleaning of outdoor surfaces and spaces | facilities managers
Plan for increased levels of cleaning & disinfecting surfaces in schools and buses. | Estimate the time necessary to meet a higher standard for daily cleaning. | janitorial staff
Plan for increased levels of cleaning & disinfecting surfaces in schools and buses. | Estimate the added supplies, materials and equipment that are needed to carry out the daily CHECK LIST for cleaning. | facilities managers
Plan for increased levels of cleaning & disinfecting surfaces in schools and buses. | Purchase disinfectant and sprayers. | administrators
Plan for increased levels of cleaning & disinfecting surfaces in schools and buses. | Purchase hand sanitizers | administrators
Purchase HEPA vaccums for each school
Plan for increased levels of cleaning & disinfecting surfaces in schools and buses. | Develop CHECK LIST for cleaning school buses | bus operators
Plan for increased levels of cleaning & disinfecting surfaces in schools and buses. | Develop training program and supervisory system for cleaning after each route. | administrators
Plan for increased levels of cleaning & disinfecting surfaces in schools and buses.
Plan for improving air quality to reduce airborne pathogens in schools and buses. | Plan for improving air quality to reduce airborne pathogens in schools and buses.
Plan for improving air quality to reduce airborne pathogens in schools and buses. | Develop CHECK LIST for maintenance and controls for air-handling units, HVAC, and windows. | building engineers
Plan for improving air quality to reduce airborne pathogens in schools and buses. | Estimate the amount and cost of supplies to implement air quality improvement maintenance and controls. | building engineers
Plan for improving air quality to reduce airborne pathogens in schools and buses. | Determine whether HVAC system has fan power to use HEPA filters (York FAQs) | building engineers
Plan for improving air quality to reduce airborne pathogens in schools and buses. | Explore bipolar ionization upstream of final filter | building engineers
Plan for improving air quality to reduce airborne pathogens in schools and buses. | Explore using UVGI add-on | building engineers
Plan for improving air quality to reduce airborne pathogens in schools and buses. | Check humidity to ensure at least 50% relative humidity | building engineers
Plan for personal health and hygiene protocols for staff in schools. | Plan for personal health and hygiene protocols for staff in schools.
Plan for personal health and hygiene protocols for staff in schools. | Develop a CHECK LIST of health and hygiene protocols for staff. To include evidence-based recommendations on: | nurses
Plan for personal health and hygiene protocols for staff in schools. | Checking body temperatures | nurses
Plan for personal health and hygiene protocols for staff in schools. | Hand washing | all persons
Plan for personal health and hygiene protocols for staff in schools. | Oxygen checks | nurses
Plan for personal health and hygiene protocols for staff in schools. | Wearing masks | all persons
Plan for personal health and hygiene protocols for staff in schools. | Sick days | all persons
Plan for personal health and hygiene protocols for staff in schools. | COVID testing | nurses
Plan for personal health and hygiene protocols for staff in schools. | Contact tracing, if incident of COVID in the school. | all persons
Plan for personal health and hygiene protocols for staff in schools. | Develop an estimate of the amount and cost for supplies and equipment needed to adhere to the recommended health and hygiene protocols for staff. | facilities managers
Plan for personal health and hygiene protocols for staff in schools. | Replace lavatory fixtures with fixtures with sensors to reduce cleaning load and potential surface contamination. | janitorial staff
Plan for personal health and hygiene protocols for staff in schools. | Estimate amount and cost of personal protective items needed for custodians and contractors. | facilities managers
Plan for personal health and hygiene protocols for staff in schools. | Develop an estimate of the staff resources required to manage and supervise the health and hygiene protocols of staff, including: | administrators
Plan for personal health and hygiene protocols for staff in schools. | Make sure staff have the supplies, training and information they need to follow protocols. | administrators
Plan for personal health and hygiene protocols for staff in schools. | Follow up on questions and concerns of staff. | administrators
Plan for personal health and hygiene protocols for staff in schools. | Be the point of contact for staff that may need sick days. | administrators
Plan for personal health and hygiene protocols for staff in schools. | Monitor staff health and hygiene protocols, supplies and training. | administrators
Plan for personal health and hygiene protocols for staff in schools. | Provide mental health services and counseling to staff | other (specify)
Plan for personal health and hygiene protocols for students in schools and buses. | Plan for personal health and hygiene protocols for students in schools and buses.
Plan for personal health and hygiene protocols for students in schools and buses. | Develop a CHECK LIST of health and hygiene protocols for students, to include evidence-based recommendations on: | other (specify)
Plan for personal health and hygiene protocols for students in schools and buses. | Early childhood students (PK-2nd grades)
Plan for personal health and hygiene protocols for students in schools and buses. | Primary grades (3rd-5th or 6th grades)
Plan for personal health and hygiene protocols for students in schools and buses. | Middle grades (6th-8th)
Plan for personal health and hygiene protocols for students in schools and buses. | High school (9th-12th)
Plan for personal health and hygiene protocols for students in schools and buses. | Special education at various levels and grades
Plan for personal health and hygiene protocols for students in schools and buses. | Develop an estimate of the staff resources required to help teachers manage and supervise the adherence of students to health and hygiene protocols, to include: | administrators
Plan for personal health and hygiene protocols for students in schools and buses. | Making sure classrooms have the supplies and equipment needed to adhere to protocols. | administrators
Plan for personal health and hygiene protocols for students in schools and buses. | Provision of training to students and teachers on the student required protocols and student consequences for not following the protocols. | nurses
Plan for personal health and hygiene protocols for students in schools and buses. | Expand the number of hand washing stations in schools and outside of schools if appropriate. | facilities managers
Plan for personal health and hygiene protocols for students in schools and buses. | Develop an estimate of the amount and cost of personal health and hygiene supplies and equipment needed for students. | administrators
Plan for personal health and hygiene protocols for students in schools and buses. | Provide N95 masks to students? - change daily? Every other day? Weekly? | administrators
Plan for personal health and hygiene protocols for students in schools and buses. | Provide gloves to custodians for cleaning--5 (??) pairs per day | administrators
Plan for personal health and hygiene protocols for students in schools and buses. | Provide mental health services and counseling to students | other (specify)
Plan for increased levels of cleaning & disinfecting surfaces in schools and buses. | Prepare a training regime for current and new employees and contractors. | administrators | system
Plan for personal health and hygiene protocols for staff in schools. | Prepare and train a much larger cadre of substitute teachers in anticipation of potential increase in sick days required by teaching staff. | administrators

## who where when how often
who? needs to do it | where? does the task need to be done | when? does the task need to be done | how often? does the task need to be done
administrators | site, outside the building | overnight | after each use
bus operators | at building entrances | mornings | after each class
all persons | main office | midday | daily
janitorial staff | hallways | afternoon | 1 x week
facilities managers | classrooms & other instructional spaces | evening | 2-3 x week
space planner | all areas inside the building | whenever occupied | other (specify)
nurses | all instructional spaces in the building | other (specify)
outside contractor | other (specify) | for reopening
parents |  | ongoing
students
support staff
teachers
other (specify)
building engineers
community process
educators